# PocketSmart AI — Project Planning Phase

Phase 4 of 8 · Your Smart Budget & Recommendation Assistant

## 1. Objectives

Deliver a working MVP of PocketSmart AI with three planners (Home, Party, Jewelry), Gemini-powered recommendations, a responsive UI, testing results and full documentation, ready for demonstration.

## 2. Work Breakdown Structure

| WBS | Work package | Source activities |
| --- | --- | --- |
| 1 | Gemini AI setup and initialization | 1.1 Cloud access and API, 1.2 API key and limits, 1.3 prompt tuning |
| 2 | Core functionality | 2.1 Flask structure, 2.2 planner endpoints, 2.3 prompt templates with text + image |
| 3 | Backend implementation | 3.1 routes, 3.2 modular structure, 3.3 CORS and sessions, 3.4 mock API data |
| 4 | UI development | 4.1 responsive forms, 4.2 dynamic result display |
| 5 | Testing and optimization | 5.1 real-world tests, 5.2 quality evaluation, 5.3 validations, 5.4 fallbacks |
| 6 | Documentation | User guide, setup guide, API reference |
| 7 | Demonstration | Demo script, rehearsal, backup plan |

## 3. Milestones

| Milestone | Deliverable | Exit check |
| --- | --- | --- |
| M1: Gemini AI initialization | API key configured; text and image test calls succeed | Sample prompt returns a valid answer |
| M2: Backend ready | Flask app with three working endpoints and mock data | Endpoints return structured JSON |
| M3: UI integrated | Three forms and results view connected to backend | End-to-end flow works for each planner |
| M4: Tested and optimized | Test report, validations, fallbacks | Budget adherence target met |
| M5: Documented and demo-ready | Documentation set and demo script | Rehearsal completed |

## 4. Schedule (suggested 5-week plan)

Dates are placeholders; adjust to your start date and team size.

| Week | Focus | Key outputs |
| --- | --- | --- |
| 1 | Ideation, requirements, design; Gemini setup (M1) | Phase 1–3 documents, working API key, prompt drafts |
| 2 | Backend core (M2) | Flask structure, routes, services, mock catalogs |
| 3 | Frontend and integration (M3) | Three planner forms, result display, image upload |
| 4 | Testing and optimization (M4) | Test cases run, prompt tuning, validations, fallbacks |
| 5 | Documentation and demo (M5) | User guide, final report, demo rehearsal |

## 5. Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project lead | Scope, schedule, reviews, demo owner |
| AI / prompt engineer | Gemini setup, prompt templates, output quality |
| Backend developer | Flask routes, services, validation, mock data |
| Frontend developer | HTML/CSS/JS forms, results UI |
| Tester / documenter | Test cases, defect log, documentation |

For a smaller team, combine roles; each person should still own at least one work package.

## 6. Tools and Environment

- Python 3, Flask, Flask-CORS, Google Gemini SDK

- Google AI Studio for API key and prompt experiments

- Git and GitHub for version control

- VS Code, Postman or curl for API testing

- Shared task board (Trello, Jira or GitHub Projects)

## 7. Risk Register

| ID | Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| R1 | Gemini quota or rate limit hit | Medium | High | Usage limits, caching, retry with backoff | AI engineer |
| R2 | AI exceeds budget or returns bad JSON | High | High | Strict prompt, validator, fallbacks | Backend developer |
| R3 | Retail APIs unavailable | High | Medium | Mock catalogs for MVP | Project lead |
| R4 | Model name or version changes | Medium | Medium | Model ID in configuration | AI engineer |
| R5 | API key leaked | Low | High | Environment variables, .gitignore, key rotation | Backend developer |
| R6 | Schedule slip | Medium | Medium | Weekly check-ins, cut Should items first | Project lead |

## 8. Dependencies

- Google account with Gemini API access before any AI work starts.

- Mock catalogs before AI prompts can reference products.

- Backend endpoints before the UI can be integrated.

- Stable endpoints before formal testing.

## 9. Communication and Quality Plan

- Short weekly review of progress against milestones.

- Pull requests reviewed by at least one other member.

- Defects tracked in a shared log with severity and owner.

- Definition of done: code reviewed, tested against acceptance criteria and documented.

## 10. Scope Control

| Priority | Items |
| --- | --- |
| Must | Three planners, Gemini integration, budget validation, structured result display |
| Should | Fallbacks, session memory, polished UI states |
| Could | Saved plans, share link, regional languages |
| Won't (MVP) | Payments, live price scraping, price alerts |